## TestCase
Product Name |  | BD Shop | TC Start Date | 2024-06-09 | TC Execution Start Date | 2024-06-12 |  |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 2024-06-12 | TC Execution End Date | 2024-06-12 |  |  |  |  | PASS | 54
Epic |  |  | Test Case Developed By |  | Browser (tested) | Yes |  |  |  |  | FAIL | 6
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 60
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'BD Shop' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Check red asterisk beside mandatory field |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check alignment of the fields |  |  | Passed
7 |  |  |  | Checkbox beside 'Sign Up for Newsletter' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Check checkbox beside 'Sign Up for Newsletter' |  |  | Passed
8 |  |  |  | Checkbox beside 'Remember Me' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check checkbox beside 'Remember Me' |  |  | Passed
9 |  |  |  | Checking 'Remember Me' checkbox is not enabled by default | Should not be enabled by default | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check 'Remember Me' checkbox | Remember Me checkbox error |  | Failed
10 |  | Functional Testing |  | Keeping mandatory fields blank | Should be as per the requirement | Sholud not allow user to register and pop an error message | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3.Keep mandatory fields blank |  |  | Passed
11 |  |  |  | Checking firstname and lastname field is case insensitive | Should accept the provided input | Found as per expectation | AbbCCdd uuXXggDD | 1. Goto the URL https://www.bdshop.com/ 2. Input AbbCCdd and uuXXggDD in firstname and lastname field |  |  | Passed
12 |  |  |  | Entering blank at first position in firstname and lastname field | Should not accept the provided input | Found as per expectation | Aakk kkhhQQ | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Input space at first position of firstname and lastname | First blank position error |  | Failed
14 |  |  |  | Checking alert message for all mandatory fields | Should pop an error message | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Keeping blank in each field and checking repeatedly |  |  | Passed
15 |  |  |  | Inputing firstname and lastname with special characters | Should not accept the provided input | Not found as per expectation | *&&&*()))) **###@%% | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter special characters in firstname and lastname field | Special character error |  | Failed
16 |  |  |  | Inputing firstname and lastname with numbers | Should not accept the provided input | Not found as per expectation | 66754455 7589699 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter numbers in firstname and lastname field | Numbers error |  | Failed
17 |  |  |  | Inputing firstname and lastname with decimal numbers | Should not accept the provided input | Not found as per expectation | 78.7568.99 87.9878.4 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter decimal numbers in firstname and lastname field | Decimal numbers error |  | Failed
18 |  |  |  | Inputing firstname and lastname with alphanumeric characters | Should accept the provided input | Found as per expectation | John88 lizz44 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter alphanumeric characters in firstname and lastname field |  |  | Passed
19 |  |  |  | Inputing firstname and lastname with alphabets | Should accept the provided input | Found as per expectation | John Austin | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter alphabets in firstname and lastname field |  |  | Passed
21 |  |  |  | Entering space between alphabets for firstname and lastname | Should accept the provided input | Found as per expectation | 01 8277 9 9 7 * | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter space between alphabets in firstname and lastname field |  |  | Passed
22 |  |  |  | Checking newsteller checkbox | Should function successfully | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Select the newsteller checkbox |  |  | Passed
23 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation with an error message | tamannasana44@gmail.com | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill the email address with already registered email |  |  | Passed
24 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation with an error message | hgfhghjgh@yuygh | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill the email address with invalid email address format |  |  | Passed
25 |  |  |  | Checking by inputing valid email format | Should accept the provided input | Found as per expectation | tamannasana44@gmail.com | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill the email address with valid email address format |  |  | Passed
26 |  |  |  | Checking password and confirm field values are masked | Should be masked | Found as per expectation | john8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter password and confirm password |  |  | Passed
27 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display a pop message | Found as per expectation | john8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter invalid combinations of characters in password and confirm password |  |  | Passed
28 |  |  |  | Inputing weak password length | Should allow user to register | Found as per expectation | hhg#k88 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter weak password length in password and confirm password |  |  | Passed
29 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation | hjfyvj%975 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter medium password length in password and confirm password |  |  | Passed
30 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | hgjkgjkjkjh!&*77 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter strong password length in password and confirm password |  |  | Passed
31 |  |  |  | Inputing different data for password and confirm password | Should not allow user to register and display a pop message | Found as per expectation | Password: john@8888 Confirm password: jnn8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter different values in password and confirm password |  |  | Passed
32 |  |  |  | Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation | john@8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter valid credentals in password and confirm password |  |  | Passed
33 |  |  |  | Selecting 'Remember Me' checkbox to disable | Should disable 'Remember Me' option | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Disable 'Remember Me' checkbox |  |  | Passed
34 |  |  |  | Checking visiting the site again by selecting 'Remember Me' | Should remember credentials | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 Remember Me: Select | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Enable 'Remember Me' 5. Visit the site again |  |  | Passed
35 |  |  |  | Checking visiting the site again by unselecting 'Remember Me' | Should not remember credentials | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 Remember Me: Unselect | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Disable 'Remember Me' 5. Visit the site again |  |  | Passed
36 |  |  |  | Checking captcha inputing invalid data | Should not accept the captcha and pop an error message | Found as per expectation | ghj8 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Fill invalid data in captcha field |  |  | Passed
37 |  |  |  | Keeping captcha field blank | Should not enable user to register and pop an error message | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Keep captcha field blank |  |  | Passed
38 |  |  |  | Checking captcha is case insensitive | Should be case insensitive | Found as per expectation | HgWy7 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Fill the captcha with upper and lower case alphabets |  |  | Passed
39 |  |  |  | Checking new captcha is generated on page reload | Should generate new captcha | Found as per expectation | v5Br | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Reload the site again |  |  | Passed
40 |  |  |  | Checking new captcha is generated adding wrong captcha | Should generate new captcha | Found as per expectation | k9nb | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Input wrong captcha |  |  | Passed
41 |  |  |  | Checking reload captcha option | Should generate new captcha | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Reload captcha |  |  | Passed
42 |  |  |  | Checking captcha inputing valid data | Should allow user to register | Found as per expectation | m433 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Input valid captcha |  |  | Passed
43 |  |  |  | Checking registration with invalid email address | Should not allow user to register and pop an error message | Not found as per expectation | Firstname: john Lastname: smith Email: john@gd.com Password: jj77 Confirm Password: jj77 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Create an Account' | Invalid email address error |  | Failed
44 |  |  |  | Checking registration button with valid credentials | Should allow user to register | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' |  |  | Passed
45 |  |  |  | Checking confirmation mail sent to the registered email | Sent successfully | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' 5. Check mail and confirm account |  |  | Passed
46 |  |  |  | Checking 'Sign in with Facebook' | Should allow user to register | Found as per expectation | Click on 'Sign in with Facebook' | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Click on 'Sign in with Facebook' |  |  | Passed
47 |  |  |  | Checking 'Sign in with Google' | Should allow user to register | Found as per expectation | Click on 'Sign in with Google' | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Click on 'Sign in with Google' |  |  | Passed
48 |  | Usability Testing |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | jane9999 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
49 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter tab in every field |  |  | Passed
50 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter enter in every field |  |  | Passed
51 |  | Functionality Testing | Sign In | Keeping email and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3. Keep both the fields blank |  |  | Passed
52 |  |  |  | Checking if the data in password is masked | Should be masked | Found as per expectation | john@8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3. Input values in password field and check if it is masked |  |  | Passed
53 |  |  |  | Checking login wrong credentials in email and password field | Should not allow user to login and display an error messeage | Found as per expectation | fgcfh@nndj.com hdjui44 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3. Input invalid credentials in email and password field |  |  | Passed
54 |  |  |  | Checking login valid credentials in email and password field | Should allow user to register | Found as per expectation | Email: janev4141@gmail.com Password: jane@2222 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3. Input valid credentials in email and password field |  |  | Passed
55 |  |  |  | Verifying ‘Forgot Password’ functionality | Should sent an email for recovering password | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check email |  |  | Passed
56 |  |  |  | Checking by selecting ‘Forgot Password’ multiple times | Account should be temporarily restricted and a message should be displayed | Found as per expectation with a message | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' multiple times |  |  | Passed
57 |  |  |  | Verifying change the password link is sent to valid email address | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email |  |  | Passed
58 |  |  |  | Verifying the functionality of 'Set a New Password' | Should provide a new input for setting new password | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' |  |  | Passed
59 |  |  |  | Enabling the 'Show Password' checkbox of 'Set a New Password' | Password should be dispayed | Found as per expectation | Email: janev4141@gmail.com Password: jane@4444 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enable 'Show Password' checkbox |  |  | Passed
60 |  |  |  | Verifying inputing old password on 'Set a New Password' | Should not allow user to login and display an error message | Found as per expectation with an error message | Email: janev4141@gmail.com Password: jane@2222 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter old password |  |  | Passed
61 |  |  |  | Verifying login with the newly changed password | Should allow user to login | Found as per expectation | Email: janev4141@gmail.com Password: jane@4444 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on login |  |  | Passed
62 |  |  |  | Checking if the link gets dissolved setting a new password | Link should get dissolved | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on 'Create New password' |  |  | Passed
|  |  | Improvement Scopes | 'Remember Me' checkbox should be selected according to user
A maximum length of the password should be defined
Place 'Whats this?' below 'Remember Me'
Place 'Forgot your password' link below Password field
Negative test

## Copy of TestCase
Product Name |  | BD Shop | TC Start Date | 15/09/2022 | TC Execution Start Date | 17/09/2022 |  |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date | 16/09/2022 | TC Execution End Date | 18/09/2022 |  |  |  |  | PASS | 54
Epic |  |  | Test Case Developed By | Tamanna Zubairi Sana | Browser (tested) | Yes |  |  |  |  | FAIL | 8
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 62
#SL | Module | Type of Testing | Features | Test Cases Descripton | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  |  |  | Found as per expectation | Chrome Internet Explorer Mozilla Firefox Microsoft Edge Opera Mini | 1. Goto different browsers 2. Search 'BD Shop' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up |  |  | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Check red asterisk beside mandatory field |  |  | Passed
5 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Hover over every fields |  |  | Passed
6 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check alignment of the fields |  |  | Passed
7 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Check checkbox beside 'Sign Up for Newsletter' |  |  | Passed
8 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check checkbox beside 'Remember Me' |  |  | Passed
9 | [5 empty] | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Check 'Remember Me' checkbox | Remember Me checkbox error |  | Failed
10 |  | Functional Testing |  |  |  | Sholud not allow user to register and pop an error message | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3.Keep mandatory fields blank |  |  | Passed
11 | [5 empty] | Found as per expectation | AbbCCdd uuXXggDD | 1. Goto the URL https://www.bdshop.com/ 2. Input AbbCCdd and uuXXggDD in firstname and lastname field |  |  | Passed
12 | [5 empty] | Found as per expectation | Aakk kkhhQQ | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Input space at first position of firstname and lastname | First blank position error |  | Failed
13 | [5 empty] | Not found as per expectation | BBggn qgKnnj | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Input space at last position of firstname and lastname | Last blank position error |  | Failed
14 | [5 empty] | Not found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Keeping blank in each field and checking repeatedly |  |  | Passed
15 | [5 empty] | Not found as per expectation | *&&&*()))) **###@%% | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter special characters in firstname and lastname field | Special character error |  | Failed
16 | [5 empty] | Not found as per expectation | 66754455 7589699 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter numbers in firstname and lastname field | Numbers error |  | Failed
17 | [5 empty] | Not found as per expectation | 78.7568.99 87.9878.4 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter decimal numbers in firstname and lastname field | Decimal numbers error |  | Failed
18 | [5 empty] | Found as per expectation | John88 lizz44 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter alphanumeric characters in firstname and lastname field |  |  | Passed
19 | [5 empty] | Found as per expectation | John Austin | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter alphabets in firstname and lastname field |  |  | Passed
20 | [5 empty] | Not found as per expectation | jjs,iioo jjdh,dhu | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter comma alphabets in firstname and lastname field | Comma between alphabets error |  | Failed
21 | [5 empty] | Found as per expectation | 01 8277 9 9 7 * | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter space between alphabets in firstname and lastname field |  |  | Passed
22 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Select the newsteller checkbox |  |  | Passed
23 | [5 empty] | Found as per expectation with an error message | tamannasana44@gmail.com | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill the email address with already registered email |  |  | Passed
24 | [5 empty] | Found as per expectation with an error message | hgfhghjgh@yuygh | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill the email address with invalid email address format |  |  | Passed
25 | [5 empty] | Found as per expectation | tamannasana44@gmail.com | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill the email address with valid email address format |  |  | Passed
26 | [5 empty] | Found as per expectation | john8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter password and confirm password |  |  | Passed
27 | [5 empty] | Found as per expectation | john8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter invalid combinations of characters in password and confirm password |  |  | Passed
28 | [5 empty] | Found as per expectation | hhg#k88 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter weak password length in password and confirm password |  |  | Passed
29 | [5 empty] | Found as per expectation | hjfyvj%975 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter medium password length in password and confirm password |  |  | Passed
30 | [5 empty] | Found as per expectation | hgjkgjkjkjh!&*77 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter strong password length in password and confirm password |  |  | Passed
31 | [5 empty] | Found as per expectation | Password: john@8888 Confirm password: jnn8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter different values in password and confirm password |  |  | Passed
32 | [5 empty] | Found as per expectation | john@8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter valid credentals in password and confirm password |  |  | Passed
33 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Disable 'Remember Me' checkbox |  |  | Passed
34 | [5 empty] | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 Remember Me: Select | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Enable 'Remember Me' 5. Visit the site again |  |  | Passed
35 | [5 empty] | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 Remember Me: Unselect | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Disable 'Remember Me' 5. Visit the site again |  |  | Passed
36 | [5 empty] | Found as per expectation | ghj8 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Fill invalid data in captcha field |  |  | Passed
37 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Keep captcha field blank |  |  | Passed
38 | [5 empty] | Found as per expectation | HgWy7 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Fill the captcha with upper and lower case alphabets |  |  | Passed
39 | [5 empty] | Found as per expectation | v5Br | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Reload the site again |  |  | Passed
40 | [5 empty] | Found as per expectation | k9nb | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Input wrong captcha |  |  | Passed
41 | [5 empty] | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Reload captcha |  |  | Passed
42 | [5 empty] | Found as per expectation | m433 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4. Input valid captcha |  |  | Passed
43 | [5 empty] | Not found as per expectation | Firstname: john Lastname: smith Email: john@gd.com Password: jj77 Confirm Password: jj77 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Create an Account' | Invalid email address error |  | Failed
44 | [5 empty] | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' |  |  | Passed
45 | [5 empty] | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with valid credentials 4.Click 'Create an Account' 5. Check mail and confirm account |  |  | Passed
46 | [5 empty] | Found as per expectation | Click on 'Sign in with Facebook' | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Click on 'Sign in with Facebook' |  |  | Passed
47 | [5 empty] | Found as per expectation | Click on 'Sign in with Google' | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Click on 'Sign in with Google' |  |  | Passed
48 |  | Usability Testing |  |  |  | Functioning successfully | jane9999 | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Copy paste text in every field |  |  | Passed
49 |  |  |  |  | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter tab in every field |  |  | Passed
50 |  |  |  |  | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Enter enter in every field |  |  | Passed
51 |  | Functionality Testing | Sign In |  | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3. Keep both the fields blank |  |  | Passed
52 |  |  |  |  | Should be masked | Found as per expectation | john@8888 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3. Input values in password field and check if it is masked |  |  | Passed
53 |  |  |  |  | Should not allow user to login and display an error messeage | Found as per expectation | fgcfh@nndj.com hdjui44 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3. Input invalid credentials in email and password field |  |  | Passed
54 |  |  |  |  | Should allow user to register | Found as per expectation | Email: janev4141@gmail.com Password: jane@2222 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3. Input valid credentials in email and password field |  |  | Passed
55 |  |  |  |  | Should sent an email for recovering password | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check email |  |  | Passed
56 |  |  |  |  | Account should be temporarily restricted and a message should be displayed | Found as per expectation with a message | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' multiple times |  |  | Passed
57 |  |  |  |  | Should be sent to valid email address | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email |  |  | Passed
58 |  |  |  |  | Should provide a new input for setting new password | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' |  |  | Passed
59 |  |  |  |  | Password should be dispayed | Found as per expectation | Email: janev4141@gmail.com Password: jane@4444 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enable 'Show Password' checkbox |  |  | Passed
60 |  |  |  |  | Should not allow user to login and display an error message | Found as per expectation with an error message | Email: janev4141@gmail.com Password: jane@2222 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter old password |  |  | Passed
61 |  |  |  |  | Should allow user to login | Found as per expectation | Email: janev4141@gmail.com Password: jane@4444 | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on login |  |  | Passed
62 |  |  |  |  | Link should get dissolved | Found as per expectation | N/A | 1. Goto the URL https://www.bdshop.com/ 2. Click on login button at the right corner 3.Click on 'Forgot Password' 4. Check the registered email 5. Click on 'Set up a New Password' 6. Enter new password 7. Click on 'Create New password' |  |  | Passed
Improvement Scopes
Negative test

## Sheet2
TC01